## Voyage Plan
R/V Brooks McCall
Voyage Plan
2010-06-16
General
Client: |  |  |  | BP Oil Spill Trustees
Purpose/Job: |  |  |  | J10852 Leg 8
Area: |  |  |  | Block 252 Mississippi Canyon, GOM
From: |  | Fourchon, La | [6 empty] | To: | Fourchon, La.
Estimated Duration: |  |  |  |  | 5 |  | Days |  |  | 230 | Miles
Estimated Consumables
Fuel |  |  |  | Required: |  | 750 |  | gal/day |  |  | On Board: |  | 30842 | gal.
Lube Oil |  |  |  | Required: |  | 5 |  | gal./day |  |  | On Board: |  | 788 | gal.
Water |  |  |  | Required: |  | 1200 |  | gal./day |  |  | On Board: |  | 36000 | gal.
Plan Implementation
|  |  | Course to be Steered |  |  |  |  | 135 degrees to 1st waypoint from Fourchon Sea Buoy
|  |  | Distance on Course |  |  |  |  | 34 nm to 1st site from Fourchon Sea Buoy
Departure |  |  | Tidal Depth / Currents |  |  |  |  | N/A
2010-06-16 |  |  | Port Clearance |  |  |  |  | N/A
|  |  | Pilot Requirements |  |  |  |  | N/A
|  |  | NTMs |  |  |  |  | Up to date through 24/10
Enroute |  |  | Safe Distances |  |  |  |  | N/A
|  |  | Prohibited Zones |  |  |  |  | Loop Terminal (Boundaries on KNav plotter, 1116A)
|  |  | Critical Depth Areas |  |  |  |  | N/A
|  |  | Contingency Ports |  |  |  |  | N/A
|  |  | NTMs |  |  |  |  | Up to date through 24/10
|  |  | Course to be Steered |  |  |  |  | 215 degrees from last waypint to Fourchon Sea Buoy
|  |  | Distance on Course |  |  |  |  | 34 nm from last waypoint from Fourchon Sea Buoy
Est. Arrival |  |  | Pier / Anchorage |  |  |  |  | Fouchon
2010-06-20 |  |  | Agent |  |  |  |  | N/A
|  |  | Tidal Depth / Currents |  |  |  |  | N/A
|  |  | Customs / Clearance |  |  |  |  | N/A
|  |  | Pilot Requirements |  |  |  |  | N/A
|  |  | NTMs |  |  |  |  | Up to date through 24/10
Charts and Publications
Departure | [5 empty] | 1116A, 11365
Enroute-Contingency | [5 empty] | 1116A, 1115A, 11365, 11361
Arrival | [5 empty] | 1116A, 11365
Waypoints
# | Location ID | [5 empty] | Latitude |  |  |  |  | Longitude
1 | Point North of Sea Buoy | [5 empty] | 29° 04.0625' N |  |  |  |  | 90° 13.7500' W
2 | WPT002 | [5 empty] | 29° 01.0150' N |  |  |  |  | 90° 13.5000' W
3 | WPT003 | [5 empty] | 29° 00.3500' N |  |  |  |  | 90° 13.2100' W
4 | WPT004 | [5 empty] | 28° 56.5000' N |  |  |  |  | 90° 11.8000' W
5 | WPT005 | [5 empty] | 28° 51.5000' N |  |  |  |  | 90° 06.7000' W
6 | WPT006 | [5 empty] | 28° 49.5000' N |  |  |  |  | 90° 03.5000 W
7 | WPT007 | [5 empty] | 28° 37.3500' N |  |  |  |  | 89° 33.0000 W
8 | WPT008 | [5 empty] | 28° 39.0000' N |  |  |  |  | 89° 09.5000 W
9 | Mississippi Canyon 252 | [5 empty] | 28° 44.0000' N |  |  |  |  | 88° 25.0000' W
Operational Contraints
Type of Operation |  |  |  | Special Considerations
Sampling etc. |  |  |  | SIMOPS with other vessels and operations in the area.
Required Reports
Daily Position Report at Midnight
Email to: |  | DPR Group
LAT |  | Position latitude
LON |  | Position longitude
FC |  | Fuel Consumed in the Last 24 hrs.
FOROB |  | Fuel Remaining on Board
LOC |  | Lube Oil Consumed in the Last 24 hrs.
LOROB |  | Lube Oil Remaining On Board
WC |  | Water Consumed in the Last 24 hrs.
WROB |  | Water Remaining On Board
ETA |  | Estimated Time of Arrival at Next Waypoint or Port
Client Reports
Email to: |  |  |  | Dr. Jim Brooks, DPR Group
Responsibility of |  |  |  | James Howell
Frequency |  |  |  | Each day - 24 hrs.
Format / Content |  |  |  | Client Specific
Incident Reports
Email to: |  | russellputt@tdi-bi.com, russellputt@gmail.com, DPR Group
Responsibility of |  |  |  | Captain
Send by |  |  |  | Within 24 hrs. of Incident
Format / Content |  |  |  | TDI HSE Reporting Form
Master:
R/V Brooks McCall
Crew Manifest
2010-06-16
FD = Foc'sle Deck | [5 empty] | MD = Main Deck | [5 empty] | LL = Lower Level
# | Name | [7 empty] | Title |  |  |  |  | Room #
1 | Opel, Chris | [7 empty] | Master |  |  |  |  | F3
2 | Majni, Geno | [7 empty] | Chief Mate |  |  |  |  | F2
3 | Kamal, Wasib | [7 empty] | Engineer |  |  |  |  | F1
4 | McCluskey, Ben | [7 empty] | Oiler |  |  |  |  | LL16
5 | Felix, Frank | [7 empty] | A/B |  |  |  |  | LL17
6 | Majni, Ann | [7 empty] | OS |  |  |  |  | F2
7 | Narcisse, Paul | [7 empty] | Cook |  |  |  |  | MD5
8 | Howell, James | [7 empty] | Party Chief |  |  |  |  | LL12
9 | Green, Billy | [7 empty] | Winch Operator |  |  |  |  | LL15
10 | Lane, Larry | [7 empty] | Deck |  |  |  |  | LL10
11 | Clark, Paul | [7 empty] | CTD Tech |  |  |  |  | LL15
12 | Stevens, Leigh | [7 empty] | EM&A |  |  |  |  | LL14
13 | Essex, Laura | [7 empty] | EM&A |  |  |  |  | MD9
14 | Lim, Hsiao | [7 empty] | LBL |  |  |  |  | MD4
15 | Wetmore, Kelly | [7 empty] | LBL |  |  |  |  | MD4
16 | O'Brien, Daniel | [7 empty] | CSS |  |  |  |  | LL11
17 | McIntyre, Claire | [7 empty] | DFO |  |  |  |  | MD9
18 | Ryan, Scott | [7 empty] | DFO |  |  |  |  | LL14
19 | Worthy, L. Dorsey | [7 empty] | EPA |  |  |  |  | LL13
20 | MochonCullura, Chris | [7 empty] | EPA |  |  |  |  | LL13
21 | Gaydos, Dana | [7 empty] | ENTRIX |  |  |  |  | MD6
22 | Susdorf, Gary | [7 empty] | ENTRIX |  |  |  |  | MD7
23 | McThenia, Andy | [7 empty] | ENTRIX |  |  |  |  | MD7
24 | Hall, Steve | [7 empty] | NOAA |  |  |  |  | LL11